## OO1 PHYSICAL
HPMES Form 4B
DEPARTMENT OF SOCIAL WELFARE AND DEVELOPMENT
FIRST QUARTERLY ACCOMPLISHMENT REPORT
FY 2022
Strategy/ Program/ Sub-Program/ Performance Indicator |  | Physical Targets |  |  |  |  | Physical Accomplishments | [20 empty] | Variance | Assessment of Variance |  |  | Reasons for Variance | Steering Measures
|  | Q1 | Q2 | Q3 | Q4 | Total | Q1 |  |  | Q2 |  |  | 1st Semester |  |  | Q3 |  |  | Q4 |  |  | 2nd Semester |  |  | Total
[7 empty] | M | F | T | M | F | T | M | F | T | M | F | T | M | F | T | M | F | T | M | F | T |  | Major | Minor | Full target Achieved
-1 |  | -2 | -3 | -4 | -5 | -6 |  |  | -7 |  |  | -8 |  |  |  | -9 |  |  |  |  | -10 | [5 empty] | (11)=(12)+(13)+(14)+(15) |  |  |  | (12)=(11)-(6) | -13 | -19
Strategic Focus 2: Improve well-being of Beneficiaries and 4Ps households through strengthened social welfare system
ORGANIZATIONAL OUTCOME 1: WELLBEING OF POOR FAMILIES IMPROVED
OUTCOME INDICATOR
1.1 | Percentage of Pantawid households with improved wellbeing
| a. 1. Survival -Baseline | - | [6 empty] | 395
| a.2. Survival to Subsistence | - | [6 empty] | -
| b.1. Subsistence - Baseline | - | [6 empty] | 79404
| b.2. Subsistence to Self-Sufficiency | - | [6 empty] | -
| c.1. Self-Sufficient - Baseline | - | [6 empty] | 20234
| c.2. Survival to Self-Sufficiency | -
1.2 | Percentage compliance of Pantawid Pamilya households on school enrolment of children | 95% | 95% | 95% | 95% | 95% | n/a | n/a | 98.7% |  |  |  | n/a | n/a | 98.7% | [9 empty] | n/a | n/a | 98.7% | 3.7% |  |  | Full target achieved | Based on compliance with education conditionality of monitored child beneficiaries from Pre-School to Senior High School in both the MCCT and RCCT (P6 2021)
1.3 | Percentage compliance of Pantawid Pamilya households on availment of health services | 95% | 95% | 95% | 95% | 95% | n/a | n/a | 98.93% |  |  |  | n/a | n/a | 98.93% | [9 empty] | n/a | n/a | 98.93% | 3.93% |  |  | Full target achieved | Based on compliance with health conditionality of monitored child beneficiaries/pregnant women in both the MCCT and RCCT. (P6 2021)
1.4 | Percentage of Pantawid Pamilya children not attending school that returned to school | TBD | TBD | TBD | TBD | TBD | n/a | n/a | 0% |  |  |  | n/a | n/a | 0% | [9 empty] | n/a | n/a | 0% |  | Major |  |  | NPMO is still identifying regional targets | NPMO will cascade the target
1.5 | Percentage of Pantawid Pamilya households not availing key health services that availed key health services | TBD | TBD | TBD | TBD | TBD | n/a | n/a | 0% |  |  |  | n/a | n/a | 0% | [9 empty] | n/a | n/a | 0% |  | Major |  |  | NPMO is still identifying regional targets | NPMO will cascade the target
1.6 | Percentage of SLP Participants involved in microenterprise | 0% | 5.469% | 60.52% | 34.01% | 100% | n/a | [5 empty] | n/a | n/a | n/a | [9 empty] | n/a | n/a | n/a |  | Major |  |  | Implementation of target will start by 2nd quarter based on plan | Accomplishment will be reported in the 2nd quarter
| Total number of SLP participants equipped to engaged in a Microenterprise | 0 | 1664 | 1664 | 1664 | 1664 | n/a | [5 empty] | n/a | n/a | n/a | [9 empty] | n/a | n/a | n/a
| No.of SLP Participants involved in microenterprise | 0 | 91 | 1007 | 566 | 1664 | n/a | [5 empty] | n/a | n/a | n/a | [9 empty] | n/a | n/a | n/a
1.7 | Percentage of SLP participants employed |  |  |  |  | n/a | n/a | [5 empty] | n/a | n/a | n/a | [9 empty] | n/a | n/a | n/a |  | Major
| Total number of SLP participants equipped to be employed |  |  |  |  | n/a | n/a | [5 empty] | n/a | n/a | n/a | [9 empty] | n/a | n/a | n/a
| No.of SLP Households Employed |  |  |  |  | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a | n/a | [9 empty] | n/a | n/a | n/a
1.8 | Percentage of completed KC-NCDDP projects that have satisfactory or better sustainability evaluation rating |  |  |  |  | TBD | n/a | n/a | n/a |  |  |  | n/a | n/a | n/a | [9 empty] | n/a | n/a | n/a |  | Major |  |  | This indicator will be measured after six (6) months from completion of projects. | Evaluation result will be reported by June 2022.
OUTPUT INDICATORS
1.1 | Number of Pantawid households provided with conditional cash grants | 106212 | 106212 | 106212 | 106212 | 106212 | n/a | n/a | 107523 |  |  |  | n/a | n/a | 107523 | [9 empty] | n/a | n/a | 107523 | 1311 |  |  | Full target achieved | Continuous validation of household replacements under Set 11 A and B as well as the increase in the number of reactivation of previously inactive households were pursued. This accomplishment is measured by the number of active households; hence data cannot be disaggregated by sex.
1.11 | Percentage of Pantawid Pamilya-related grievances resolved within established time protocol | - | - | - | - | ana | n/a | n/a | 99.2% |  |  |  | n/a | n/a | 99.2% | [9 empty] | n/a | n/a | 99.2% |  |  |  |  | Data as of March 29, 2022: Data is computed using the formula: Resolved grievances within prescribed timeline/Total resolved grievances Resolved grievances: 249 Resolved grievances within the prescribed timeline: 247
| Total No. grievances received | - | - | - | - | ana | n/a | n/a | 249 |  |  |  | n/a | n/a | 249 | [9 empty] | n/a | n/a | 249
| No. of Pantawid Pamilya-related grievances resolved within established time protocol | - | - | - | - | ana | n/a | n/a | 247 |  |  |  | n/a | n/a | 247 | [9 empty] | n/a | n/a | 247
1.12 | Percentage of re-assessed self-sufficient (Level 3) households with Transition Plan |  |  |  |  | TBD | n/a | n/a | n/a |  |  |  | n/a | n/a | n/a | [9 empty] | n/a | n/a | n/a |  |  |  |  | NPMO has not cascaded the target yet. However, the program is continuously conducting SWDI reassessment for 4Ps households.
| Number of re-assessed self-sufficient (Level 3) households |  |  |  |  | TBD | n/a | n/a | n/a |  |  |  | n/a | n/a | n/a | [9 empty] | n/a | n/a | n/a
| Number of re-assessed self-sufficient (Level 3) households with Transition Plan |  |  |  |  | TBD | n/a | n/a | n/a |  |  |  | n/a | n/a | n/a | [9 empty] | n/a | n/a | n/a
1.13 | No. of participants assisted to sustainable livelihood program | 0 | 91 | 1007 | 566 | 1664 | n/a | n/a | n/a |  |  |  | n/a | n/a | n/a | [9 empty] | n/a | n/a | n/a
| a. Total number of households who received seed capital fund and total number of households trained |  |  |  |  | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a | n/a | [9 empty] | n/a | n/a | n/a
| b. Total Number of SLP households who received employment Assistance Fund modality |  |  |  |  | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a | n/a | [9 empty] | n/a | n/a | n/a |  |  |  |  | No disaggregation of targets
| c. Total number of participants provided with livelihood assistance grants EO70 SLP Regular Zero Hunger |  | 91 | 1007 | 566 | 1664 | n/a | n/a | n/a |  |  |  | n/a | n/a | n/a | [9 empty] | n/a | n/a | n/a |  |  |  |  | Accomplishment will be reported in the 2nd quarter. Program is in Pre-implementation and Social Preparation Stage. Activities already implemented include: 1. Meetings and Trainings & 2. Review and assessment
| d. Number of participants who received complementary livelihood recovery services from partners |  |  |  |  | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a | n/a | [9 empty] | n/a | n/a | n/a |  |  |  |  | No target for this indicator
1.14 | Number of SLP projects with livelihood assets built, rehabilitated and/or protected |  |  |  |  | n/a | n/a | n/a | n/a |  |  |  | n/a | n/a | n/a | [9 empty] | n/a | n/a | n/a |  |  |  |  | No target for this indicator
1.15 | Number of communities implementing KC-NCDDP |  |  |  | 635 | 635 | n/a | n/a | n/a |  |  |  | n/a | n/a | n/a | [9 empty] | n/a | n/a | n/a |  |  |  |  | Central Office is still finalizing the regional target
| a. Region |  |  |  | 1 | 1 | n/a | n/a | n/a |  |  |  | n/a | n/a | n/a | [9 empty] | n/a | n/a | n/a
| b. Province |  |  |  | 2 | 2 | n/a | n/a | n/a |  |  |  | n/a | n/a | n/a | [9 empty] | n/a | n/a | n/a
| c. Municipality |  |  |  | 4 | 4 | n/a | n/a | n/a |  |  |  | n/a | n/a | n/a | [9 empty] | n/a | n/a | n/a
| d. Barangay |  |  |  | 64 | 64 | n/a | n/a | n/a |  |  |  | n/a | n/a | n/a | [9 empty] | n/a | n/a | n/a
1.16 | Number of KC-NCDDP sub-projects completed in accordance with technical plans and schedule |  |  |  | 64 | 64 | n/a | n/a | n/a |  |  |  | n/a | n/a | n/a | [9 empty] | n/a | n/a | n/a
1.17 | Number of households benefitted from completed KC-NCDDP sub-projects |  |  |  | 500 | 500 | n/a | n/a | n/a |  |  |  | n/a | n/a | n/a | [9 empty] | n/a | n/a | n/a
1.18 | Percentage of Pantawid Pamilya community members employed in KC-NCDDP sub-projects |  |  |  |  | TBD | n/a | n/a | n/a |  |  |  | n/a | n/a | n/a | [9 empty] | n/a | n/a | n/a |  |  |  |  | Central Office is still finalizing the regional target
| Total number of Pantawid Pamilya community members employed in KC-NCDDP projects |  |  |  |  | TBD | n/a | n/a | n/a |  |  |  | n/a | n/a | n/a | [9 empty] | n/a | n/a | n/a
| Number of Pantawid Pamilya community members |  |  |  |  | TBD | n/a | n/a | n/a |  |  |  | n/a | n/a | n/a | [9 empty] | n/a | n/a | n/a
1.19 | Total number of volunteers trained on CDD |  |  |  | 1984 | 1984 | n/a | n/a | n/a |  |  |  | n/a | n/a | n/a | [9 empty] | n/a | n/a | n/a
1.2 | No. of women volunteers trained on CDD |  |  |  | 384 | 384 | n/a | n/a | n/a |  |  |  | n/a | n/a | n/a | [9 empty] | n/a | n/a | n/a
1.21 | Percentage of paid labor jobs created by KC-NCDDP are accessed by women |  |  |  |  | TBD | n/a | n/a | n/a |  |  |  | n/a | n/a | n/a | [9 empty] | n/a | n/a | n/a |  |  |  |  | Central Office is still finalizing the regional target
1.22 | No. of family beneficiaries served through Balik Probinsya Bagong Pag-asa Program |  |  |  |  | 300 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0
1.23 | No. of community vulnerable areas (CVAs) provided with disaster response services |  |  |  |  | TBD | n/a | n/a | n/a |  |  |  | n/a | n/a | n/a | [9 empty] | n/a | n/a | n/a |  |  |  |  | Central Office is still finalizing the regional target
1.24 | No of Regional Convergence Team Meetings Conducted |  |  |  |  | ANA | n/a | n/a | 1 |  |  |  | n/a | n/a | 1 | [9 empty] | n/a | n/a | 1 | [5 empty] | Develop criteria to measure tangible output
1.24 | No of Regional Strategic Partnership Orientation and Meetings Conducted |  |  |  |  | ANA | n/a | n/a | 1 |  |  |  | n/a | n/a | 1 | [9 empty] | n/a | n/a | 1 | [5 empty] | Develop criteria to measure tangible output
| Consolidated by: |  |  |  |  | Reviewed by: | [12 empty] | Recommending Approval by: | [9 empty] | Approved by:
| NESTOR P. ESQUERO |  |  |  |  | DUCENEAH LYRA F. DELA CRUZ | [12 empty] | CHANDA T. API | [9 empty] | CEZARIO JOEL C. ESPEJO
| Planning Officer I |  |  |  |  | Planning Officer IV/ Head, Policy Development and Planning Section | [12 empty] | SWO IV/ OIC- Policy and Plans Division | [9 empty] | Regional Director
Note on E28: ====== ID#AAAAS91UBw4 (2021-12-15 08:42:26) 50% lag -Sustainable Livelihood Program FO2
Note on F28: ====== ID#AAAAS91UBw8 (2021-12-15 08:42:26) 50% lag = 4376 100% referral = 1445 -Sustainable Livelihood Program FO2

## OO1 FINANCIAL
DEPARTMENT OF SOCIAL WELFARE AND DEVELOPMENT
FIRST QUARTERLY ACCOMPLISHMENT REPORT
FY 2022
Objective/ Program/ Sub-Program/ Performance Indicator | Budget (GAA) In PHP | OBLIGATION | [9 empty] | DISBURSEMENT
|  | Amount |  |  |  |  | Percent Utilization |  |  |  |  | Amount |  |  |  |  | Percent Utilization
|  | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
Strategic Focus 2: Improve well-being of Beneficiaries and 4Ps households through strengthened social welfare system
ORGANIZATIONAL OUTCOME 1:
WELLBEING OF POOR FAMILIES IMPROVED
PANTAWID PAMILYANG PILIPINO
Grand Total | 2615191730 | 185420425 |  |  |  | 185420425 | 7.09% |  |  |  |  | 167075450 |  |  |  | 167075450 | 90.11% |  |  |  | 90.11%
Regular CCT
FO |  | 176344100 |  |  |  | 176344100 | 6.743% |  |  |  |  | 167075450 |  |  |  | 167075450 | 90.11% |  |  |  | 90.11%
Modified CCT
FO |  | 9076325 |  |  |  | 9076325 | 0.3471% |  |  |  |  | 0 |  |  |  | 0 | 0% |  |  |  | 0%
SUSTAINABLE LIVEHIHOOD PROGRAM | 49082328 | 0 |  |  |  | 0 | 0% |  |  |  |  | 0 |  |  |  | 0 | 0% |  |  |  | 0%
Current Appropriation | 32259867 | 0 |  |  |  | 0 | 0% |  |  |  |  | 0 |  |  |  | 0 | 0% |  |  |  | 0%
Continuing Appropriation | 16822461 | 0 |  |  |  | 0 | 0% |  |  |  |  | 0 |  |  |  | 0 | 0% |  |  |  | 0%
Accounts Payable (Obligated last year)
EPHAP | 4785288.29 | 1188667.11 |  |  |  | 1188667.11 | 24.84% |  |  |  | 24.84% | 454917.99 |  |  |  | 454917.99 | 38.27% |  |  |  | 38.27%
Current Appropriation | 3461201.04 | 1025617.11 |  |  |  | 1025617.11 | 21.43% |  |  |  | 21.43% | 333631.21 |  |  |  | 333631.21 | 28.07% |  |  |  | 28.07%
Continuing Appropriation | 1324087.25 | 163050 |  |  |  | 163050 | 3.407% |  |  |  | 3.407% | 121286.78 |  |  |  | 121286.78 | 10.2% |  |  |  | 10.2%
BALIK-PROBINSYA PROGRAM
FO | 51000000 | 5520000 |  |  |  | 5520000 | 10.82% |  |  |  | 10.82% | 0 |  |  |  | 0 | 0% |  |  |  | 0%
KALAHI-CIDSS | 171100000 | 85000000 |  |  |  | 85000000 | 49.68% |  |  |  | 49.68% | 76500000 |  |  |  | 76500000 | 90% |  |  |  | 90%
KAPANGYARIHAN AT KAUNLARAN SA BARANGAY (KKB)
KKB (CURRENT) | 82500000 | 0 |  |  |  | 0 | 0% |  |  |  | 0% | 0 |  |  |  | 0 | 0% |  |  |  | 0%
KKB (CONTINUING) | 85000000 | 85000000 |  |  |  | 85000000 | 49.68% |  |  |  | 49.68% | 76500000 |  |  |  | 76500000 | 90% |  |  |  | 90%
PAYAPA AT MASAGANANG PAMAYANAN (PAMANA)
PAMANA (CURRENT) | 3582063.35 | 0 |  |  |  | 0 | 0% |  |  |  | 0% | 0 |  |  |  | 0 | 0% |  |  |  | 0%
PAMANA (CONTINUING) | 17936.65 | 0 |  |  |  | 0 | 0% |  |  |  | 0% | 0 |  |  |  | 0 | 0% |  |  |  | 0%
Consolidated by: |  | Reviewed by: |  |  |  |  | Recommending Approval by: | [7 empty] | Approved by:
NESTOR P. ESQUERO |  | DUCENEAH LYRA F. DELA CRUZ |  |  |  |  | CHANDA T. API | [7 empty] | CEZARIO JOEL C. ESPEJO
Planning Officer I |  | Planning Officer IV/ Head, Policy Development and Planning Section |  |  |  |  | SWO IV/ OIC- Policy and Plans Division | [7 empty] | Regional Director

## OO2 PHYSICAL
HPMES Form 4B
DEPARTMENT OF SOCIAL WELFARE AND DEVELOPMENT
FIRST QUARTERLY ACCOMPLISHMENT REPORT
FY 2022
Strategy/ Program/ Sub-Program/ Performance Indicator |  | Physical Targets |  |  |  |  | Physical Accomplishments | [20 empty] | Variance | Assessment of Variance |  |  | Reasons for Variance | Steering Measures
|  | Q1 | Q2 | Q3 | Q4 | Total | Q1 |  |  | Q2 |  |  | 1st Semester |  |  | Q3 |  |  | Q4 |  |  | 2nd Semester |  |  | Total
[7 empty] | M | F | T | M | F | T | M | F | T | M | F | T | M | F | T | M | F | T | M | F | T
-1 |  | -2 | -3 | -4 | -5 | -6 | -7 |  |  | -8 |  |  | -9 |  |  | -10 |  |  | -11 |  |  | -12 |  |  |  |  | -13 | (14)=(13)-(6) | Major | Minor | Full target Achieved | -18 | -19
Strategic Focus 2: Improve well-being of Beneficiaries and 4Ps households through strengthened social welfare system
ORGANIZATIONAL OUTCOME 2: RIGHTS OF THE POOR AND THE VULNERABLE SECTORS PROMOTED AND PROTECTED
RESIDENTIAL AND NON-RESIDENTIAL CARE SUB-PROGRAM
OUTCOME INDICATOR
1 | Percentage of clients in residential and non-residential care facilities rehabilitated
No. of Clients Rehabilitated
Residential Care Facilities
| Reception and Study Center for Children | 6 | 6 | 6 | 6 | 24 | 15 | 6 | 21 | [15 empty] | 15 | 6 | 21 | 4 |  |  | x | The attrition is based on the refferal from LGUs and other CCAs | Services provided to the residents such as Home Life, Pshycolgical, educational, health/medical, social services. Case conferences were conducted in a monthly basis for the purspose of determing the statrus of cases and progress of the residents for identification of appropriate interventions to be provided.
| CagayanValley Regional Rehabilitation for Youth | 10 | 10 | 6 | 7 | 33 | 16 | 0 | 16 | [17 empty] | 16 | 6 |  |  | x | The attrition is based on the commitment order from the court/refferal from LGUs The reported total number of rehabilitated cases are carry over cases | The CVRRCY is continously implements the SHEPHERD programs. Conducted regular case conferences. Pre-and admission conferences until discharge. Conducted monthly helping team meetings and monthly themed activity. Every monday therapuetic community meetings conducted. Actual training on farming were also conducted on livestock, rice and vegetable production.
| Regional Haven for Women and Girls | 9 | 6 | 6 | 6 | 27 | 0 | 18 | 18 | [16 empty] | 18 | 18 | 9 |  |  | x | Difficulty on the the process of discharge and litigation of cases. Postponement of court hearings impede the fast resolution of cases. | The center continuously conducted virtual case conferences/pre-discharge/discharge conferences and monthly themed activities. Coordinated with concerned LGUs for the submission of Parental Capability Assessment Report. Continuous coordination with the Regional Prosecutor on the status of residents' cases.
OUTPUT INDICATORS:
2 | Number of Clients Served
Residential Care Facilities
| Reception and Study Center for Children | 20 | 20 | 20 | 20 | 80 | 17 | 7 | 24 | [15 empty] | 17 | 7 | 24 |  |  |  | x | A total of two residents for new addmission and 22 were carry over cases.
| Cagayan Valley Regional Rehabilitation for Youth | 40 | 30 | 30 | 10 | 110 | 32 | 0 | 32 | [22 empty] | For the 32 served residents, 8 were new admission and 24 are carry over cases
| Regional Haven for Women and Girls | 30 | 20 | 20 | 20 | 90 | 0 | 36 | 36 | [16 empty] | 36 | 36 | 6 |  |  | x | Out of 36 clients served, 6 are new admissions and 30 are carry over cases | Conduct of virtual pre-admission conference prior to admission of referred client to the center.
3 | ALOS of clients in residential facilities
| RSCC (Rehab-Based) | 209 | 209 | 209 | 209 | 209 |  |  | 144.9524 | [17 empty] | 144.9524
| RRCY (Rehab-Based) | 90 | 90 | 90 | 90 | 360 |  |  | 242.9 | [17 empty] | 144.9524
| RHWG (Rehab-Based) | 209 | 209 | 209 | 209 | 209 |  |  | 208 | [17 empty] | 208 | 1 |  |  | x |  | Continuous coordination with the Regional Prosecutor on the status of residents' cases.
4 | Percentage of facilities with standard client-staff ratio
Number of Facilities with Standard Client-Social Worker Ratio
| FO2 - ( out of 3 facilities) ( out of 3 facilities) | [29 empty] | x
| Reception and Study Center for Children | 1:10 | 1:10 | 1:10 | 1:10 | 1:10 |  |  | 1:10 | [17 empty] | 1:10
| Cagayan Valley Regional Rehabilitation for Youth | 1:8-11 | 1:8-11 | 1:8-11 | 1:8-11 | 1:8-11 |  |  | 1:10-11 | [17 empty] | 1:10-11 |  |  |  | x
| Regional Haven for Women and Girls | 1:15 | 1:15 | 1:15 | 1:15 | 1:15 |  | 1:11;1:10;1:9 | 1:11;1:10;1:9 | [17 empty] | 1:11;1:10;1:9
5 | Number of Facilities with Standard Client-Houseparent Ratio
FO2 ( out of 3 facilities)
| Reception and Study Center for Children | 1:10 | 1:10 | 1:10 | 1:10 | 1:10 |  |  | 1:10 | [17 empty] | 1:10
| Cagayan Valley Regional Rehabilitation for Youth | 1:11 | 1:11 | 1:11 | 1:11 | 1:11 |  |  | 1:16 | [17 empty] | 1:16 |  |  | x |  | There is a need augmentation of Houseparent considering the need to comply with the standard ratio. At least two additional HPs to be hired. | CVRRCY will request to the management for the additional augmentation support for the hiring of houseparents.
| Regional Haven for Women and Girls | 1:20 | 1:20 | 1:20 | 1:20 | 1:20 |  | 1:15 | 1:15 | [17 empty] | 1:15 |  |  |  | /
Supplementary Feeding Sub-Program
Outcome Indicators
7 | Percentage of malnourished children in CDCs and SNPs with improved nutritional status for the 11th Cycle Implementation | 80% | 80%
| Number of Malnourished Children (Before feeding sessions) | 5433 | 5433 |  |  | 5433 |  |  | 5433 | [17 empty] | 5433 |  | x
| a. Severely underweight to Underweight (Baseline) | 783 | 783 |  |  | 783 |  |  | 783 | [17 empty] | 783
| b. Underweight to Normal (Baseline) | 4650 | 4650 |  |  | 4650 |  |  | 4650 | [17 empty] | 4650
8 | Number of Malnourished Children with improved nutritional status (After feeding session) | 4401 | 4401 |  |  | 4401 | [25 empty] | 11th cycle implementation is still on going. The target completion is by end of April 2022. | Monitoring of distribution of goods to the LGUs and gathering of liquidation reports as well as nutritional status report.
| a. Severely underweight to Underweight (21%) | 165 | 165 |  |  | 165
| b. Underweight to Normal (81%) | 3767 | 3767 |  |  | 3767
9 | Percentage of children in CDCs and SNPs with sustained normal nutritional status (over total children served) |  | 90% |  |  | 90% | [21 empty] | 10% |  |  |  | The remaining targeted children will be monitored after the feeding activities were conducted by end of the feeding cycle
| a. Number of children in CDCs and SNPs with normal nutritional status (Upon weigh-in, before feeding) |  | 88194 |  |  | 88194
| b. Number of children in CDCs and SNPs with sustained normal nutritional status (After feeding) |  | 79375 |  |  | 79375
Output Indicators
10 | Number of children in CDCs and SNPs provided with supplementary feeding (11th Cycle) |  |  | 89712 | 89712 | 89712 |  |  | 89712
Social Welfare for Senior Citizens Sub-Program
Outcome Indicator
11 | Percentage of beneficiaries using social pension to augment daily living subsistence and medical needs | 100 | 100 | 100 | 100 | 100 | 41.81% | 58.19% | 89.98% |  |  |  | 41.81% | 58.19% | 89.98% | [9 empty] | 41.81% | 58.19% | 89.98% |  |  |  |  | The Social Pension Program targeted 229,731 original beneficiaries for the 1st quarter CY 2022 with 222,454 served beneficiaries or 96.83% accomplishment. The 14,700 additional beneficiaries was not yet included in the 1st quarter obligation to which, it will be distributed simultaneously during 2nd Quarter cash pay-out retrocative. The coastal municipality of Calayan, Cagayan schedule its payment for the First and Second Quarter of CY 2022 on April 8-13, 2022. Variance will be repayrolled during the 2nd Quarter cash pay-out CY 2022.
12 | Number of beneficiaries using social pension to augment daily living subsistence and medical needs | 244431 | 244431 | 244431 | 244431 | 244431 | 91952 | 127982 | 219934 |  |  |  | 91952 | 127982 | 219934
Output Indicators
13 | Number of senior citizens who received social pension within the quarter (For FY 2021) | 244431 |  |  |  | 244431 | 91952 | 127982 | 219934 | [18 empty] | 24497 |  |  |  | The variance includes 14,700 additional beneficiaries in the original target of 229,731. The program reached a total of 96.83 physical accomplishment. The beneficieres were not present during payouts, deceased, not in the area etc. | Replacement were made to deceased and ineligible beneficiaries. Conducted advocacy activities thru radio and tapped other staff to augment during payout.
15 | Number of centenarians provided with cash gift (FY 2021) | 15 | 15 | 15 | 15 | 60 |  | 4 | 4 | [16 empty] | 4 | 4 | 11 | x |  |  | The remaining 11 centenrain applicants will be paid for the month of April 2022, while 16 will be process for the 2nd quarter to complete the 30 centenarian target. completion and retieval of documents still awaiting to complete the requirement for eligibility to received the beneifits under RA 10868 or Centenarian Act of 2016. | Continous provision of technical assistance to partner LGUs on the requirments for the said benefits. attendance to radio guesting for the advocacy measures.
Protective Program for Individuals, Families and Communities in Need or in Crisis Sub-Program
Outcome Indicator
16 | Percentage of clients who rated protective services provided as satisfactory or better (AICS)
17 | Percentage of clients who rated protective services provided as satisfactory or better (Minors Travelling Abroad) | 100% | [6 empty] | 100%
Output Indicator
| Number of minors traveling abroad issued with travel clearance (Minors Travelling Abroad) (Minors Travelling Abroad) | 96 |  |  |  |  | 46 | 50 | 96
Output Indicators
18 | Number of beneficiaries served through AICS |  |  |  |  | 21260
| Type of Assistance | [5 empty] | 4012 | 6494 | 10506 | [18 empty] | 10502
| a. Medical Assistance | 4830 |  |  |  |  | 1388 | 3442 | 4830 | [22 empty] | The serve clients reported for the 1st Quarter came from the currents funds of CY 2022. A total of 92,590 clints served for the continuing funds. | Continous payout is currently conducted. Encoding of the served clients thru database of AICS .
| b. Burial Assistance | 536 |  |  |  |  | 155 | 381 | 536
| c. Educational Assistance | 1040 |  |  |  |  | 353 | 687 | 1040
| d. Transportation Assistance | 31 |  |  |  |  | 11 | 20 | 31
| e. Food Assistance | 338 |  |  |  |  | 156 | 182 | 338
f. Non-Food Assistance
| g. Other Cash Assistance for Support Services | 3731 |  |  |  |  | 1949 | 1782 | 3731
h. Psychosocial
i. Referral
| Client Category | [5 empty] | 4012 | 6494 | 10506
| Family Head and Other Needy Adult (FHONA) | 2586 |  |  |  | 2586 | 2586 |  | 2586
| Women in Especially Difficult Circumstances (WEDC) | 4220 |  |  |  | 4220 |  | 4220 | 4220
| Children in Need of Special Protection (CNSP) | 5 |  |  |  | 5 |  | 5 | 5
| Youth in Need of Special Protection (YNSP) | 1899 |  |  |  | 1899 | 738 | 1161 | 1899
| Senior Citizen (SC) | 1776 |  |  |  | 1776 | 676 | 1100 | 1776
| Persons With Disability (PWD) | 15 |  |  |  | 15 | 7 | 8 | 15
| Persons Living with HIV-AIDS (PLHIV) | 5 |  |  |  | 5 | 5 |  | 5
Assistance to Communities in Need (ACN)
21 | Construction/ Repair of Day Care Center and Senior Citizen Center through Assistance to Communities in Need
Number of subprojects completed
Number of beneficiaries served through ACN
Output Indicators
Number of children served through Alternative Family Care Program
27 | Number of children issued with CDCLAA | 3 | 5 | 5 | 3 | 16 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 16 | x |  |  | Difficulty in retrieving the necessary requirements from LGUs and other regions. | Close coordination and follow-up of requirements needed from concerned partner LGUs/ CCAs to facilitate needed documents issuance of CDCLAA. As part of the catch up plan the program owners agreed to deliver at least 1 CDLAA per case worker per semester as indicated in thier IPCs.
28 | Number of eligible children placed under foster care provided with subsidy | 57 | 57 | 57 | 57 | 57 | 12 | 21 | 33 |  |  |  | 12 | 21 | 33 | [9 empty] | 12 | 21 | 33 | 24 | x |  |  | A total of 60 actual of children under foster care. However, per assessment only 33 children are eligible to be provided with susbsidy. Hence, the variance of 24 is due to to the limited number of eligible children assessed to be provided with subsidy | Re-assessment of the eligible children placed under foster care for the provision of foster care subsidy. The assessment will be dependent on the monitoring of the status of cases and new cases reffered to the program.
| Number of children placed under foster care | 4 | 6 | 7 | 5 | 22 | 0 | 1 | 1 |  |  |  | 0 | 1 | 1 | [9 empty] | 0 | 1 | 1 | 21 | x |  |  | No referrals made from Local Government Units, Regional Caring Facilities and Child Caring Agencies | Close coordination with LGUs/CCAs for referral of eligible children for foster placement.
Social Welfare for Distressed Overseas Filipinos and Trafficked Persons Sub-Program
Outcome
29 | Percentage of assisted individuals who are reintegrated to their families and communities
| Trafficked Persons | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% |  |  |  | 0% | 100% | 100% | [9 empty] | 0 | 100% | 100% | 0 |  |  | x |  | Close coordination with the Inter-Agency Council Against Trafficking Region 02 (RIACAT 02) and with LSWDOs regarding the monitoring of old clients and referral of new clients. Celebrated International Day Against Trafficking thru zumba and motorcade and provision of IEC materials to member agencies of the IACAT R02
| Distressed Overseas Filipinos and Families | 100% | 100% | 100% | 100% | 100% | 38 | 62 | 100 |  |  |  | 29 | 47 | 76 | [9 empty] | 29 | 47 | 76 |  |  |  | x | Limited number of walk-in and referred clients under ISSO | Augmentation in the management of One-Stop-shop DSWD Airport Team in NAIA Terminals paved the way to cater more clients under ISSO
Output
30 | Number of trafficked persons provided with social welfare services | 5 |  |  |  | 55 | 0 | 5 | 5 |  |  |  | 0 | 5 | 5 | [9 empty] | 0 | 5 | 5 |  |  |  | x | No reported cases and reffered of traffciking in persons | Conducted CY 2022 1st Quarter IACAT Meeting on April 5, 2022. The next meeting is scheduled on May 2022 for the preparation of the World Day Against trafficking this July 2022
31 | Number of distressed and undocumented overseas Filipinos provided with social welfare services | 76 |  |  |  | 313 | 29 | 47 | 76 |  |  |  | 29 | 47 | 76 | [9 empty] | 29 | 47 | 76 |  |  |  | x | Limited number of walk-in and referred clients under ISSO | The focal person provided augmentation in the management of One-Stop-shop DSWD Airport Team in NAIA Terminals paved the way to cater more clients under ISSO on February 28, 2022 to April 8, 2022.
Consolidated by: | [6 empty] | Reviewed by | [18 empty] | Recommending Approval: | [5 empty] | Approved by:
AL V. DELA CRUZ | [6 empty] | DULCENEAH LYRA F. DELA CRUZ | [18 empty] | CHANDA T. API | [5 empty] | CEZARIO JOEL C. ESPEJO
Planning Officer II | [6 empty] | Planning Officer IV, PDPS Head | [18 empty] | SWO IV/OIC Chief, PPD | [5 empty] | Regional Director

## OO2 FINANCIAL
DEPARTMENT OF SOCIAL WELFARE AND DEVELOPMENT
FIRST QUARTERLY ACCOMPLISHMENT REPORT
FY 2022
Objective/ Program/ Sub-Program/ Performance Indicator | Budget (GAA) | OBLIGATION | [9 empty] | DISBURSEMENT
|  | Amount |  |  |  |  | Utilization Rate |  |  |  |  | Amount |  |  |  |  | Utilization Rate
|  | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | REMARKS
Strategic Focus 2: Improve well-being of Beneficiaries and 4Ps households through strengthened social welfare system
ORGANIZATIONAL OUTCOME 2:
RIGHTS OF THE POOR AND THE VULNERABLE SECTORS PROMOTED AND PROTECTED
A. RESIDENTIAL AND NON-RESIDENTIAL CARE SUB-PROGRAM
Residential and Non-Residential Care Facilities
Current Funds
Regional Haven for Women and Girls | 6998126 | 2168372.23 |  |  |  | 2168372.23 | 30.985 |  |  |  |  | 1312700 |  |  |  | 1312700 | 60.5385
Reception and Study Center for Children | 6638093 | 3041543.7 |  |  |  | 3041543.7 | 45.8195 |  |  |  |  | 2060652.68 |  |  |  | 2060652.68 | 67.7502
Cagayan Valley Regional Rehabilitation for Children | 8278781 | 5262693.2 |  |  |  | 5243060.69 | 63.3313 |  |  |  |  | 3937898.12 |  |  |  | 3937898.12 | 74.8267
Continuing Funds
Regional Haven for Women and Girls | 264761.68 | 153353.58 |  |  |  | 153353.58 | 57.9214 |  |  |  |  | 121347.62 |  |  |  | 121347.62 | 79.1293
Reception and Study Center for Children | 215752.04 | 117748.51 |  |  |  | 117748.51 | 54.5759 |  |  |  |  | 102426.34 |  |  |  | 102426.34 | 86.9874
Cagayan Valley Regional Rehabilitation for Children | 3719170 | 101047.54 |  |  |  | 101047.54 | 2.7169 |  |  |  |  | 61892 |  |  |  | 61892 | 61.2504
B. Supplementary Feeding Sub-Program
Supplementary Feeding Program
11 Cycle Implementation (Contunuing Funds) | 176266200 | 176266200 |  |  |  | 176266200 | 100% |  |  |  |  | 176266200 |  |  |  | 176266200 | 100% |  |  |  |  | 53% Liquidation Rate (92,649,830.12
(12th Cycle Implementation) Current Funds | 170309760 | [20 empty] | No obligation and disbursement for 12th cycle yet. (11th cycle is still on going.)
Bangsamoro Umpungan sa Nutrisyon Program (BangUN)
ARMM
C. Social Welfare for Senior Citizens Sub-Program
Social Pension for Indigent Senior Citizens
FO2 | 1466586000 | 366646500 |  |  |  | 366646500 | 25% |  |  |  | 25% | 329901000 |  |  |  | 329901000 | 89.98% |  |  |  | 89.98%
Implementation of Centenarians Act of 2016
FO2 | 6000000 | 1600000 |  |  |  | 1600000 | 26.6667 |  |  |  | 26.6% | 400000 |  |  |  | 400000 | 6.6667 |  |  |  | 6.67%
D. Protective Program for Individuals, Families and Communities in Need or in Crisis Sub-Program
Protective Services Program AICS
Regular AICS | 415000000 | 320254699.97 |  |  |  | 320254699.97 | 77.17 |  |  |  | 77.17 | 33801575.41 |  |  |  | 33801575.41 | 10.55
Lingap at Gabay Para sa May Sakit (LinGaP sa MaSa)
FO
Assistance to Communities in Need (ACN)
FO
Comprehensive Program for Street Children, Street Families and Badjaus
FO
Alternative Family Care Program
Foster Subsidy (Continuing) | 890100 | 776000 |  |  |  | 776000 | 87.1812 |  |  |  | 87.1812 | 776000 |  |  |  | 776000 | 100
Foster Subsidy (Current) | 5544000 | 0 |  |  |  |  | 0 |  |  |  |  | 0
E. Social Welfare for Distressed Overseas Filipinos and Trafficked Persons Sub-Program
Recovery and Reintegration Program For Traffick Persons (RRPTP) | 310000 | 0 | [19 empty] | Financial Assistance provided was charged under CIU
Services to Overseas Filipinos and their Familes (International Social Services Office - ISSO)
Processing Center for Displaced person (PCDP)
Consolidated by: | Reviewed by | [5 empty] | Recommending Approval: | [8 empty] | Approved by:
AL V. DELA CRUZ | DULCENEAH LYRA F. DELA CRUZ | [5 empty] | CHANDA T. API | [8 empty] | CEZARIO JOEL C. ESPEJO
Planning Officer II | Planning Officer IV, PDPS Head | [5 empty] | SWO IV/OIC Chief, PPD | [8 empty] | Regional Director
Note on A16: ====== ID#AAAATUWBYPQ Aiza Garcia (2021-12-23 03:39:30) good day po, next year po follow po natin wfp na binigay ko per centers mga ma'am para wala na pong over utilization. salamat =)
Note on A20: ====== ID#AAAATUWBYPQ Aiza Garcia (2021-12-23 03:39:30) good day po, next year po follow po natin wfp na binigay ko per centers mga ma'am para wala na pong over utilization. salamat =)

## OO3 PHYSICAL
DEPARTMENT OF SOCIAL WELFARE AND DEVELOPMENT
FIRST QUARTER ACCOMPLISHMENT REPORT
FY 2022
Strategy/ Program/ Sub-Program/ Performance Indicator |  | Physical Targets |  |  |  | Physical Accomplishments | [6 empty] | Annual Total | Variance | Assessment of Variance |  |  | Reasons for Variance | Steering Measures/ Remarks
|  | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | 1st Semester | Q3 | Q4 | 2nd Semester
-1 |  | -2 | -3 | -4 | -5 | -6 | [6 empty] | (11)=(7)+(8)+(9)+(10) | (12)=(11)-(6) | Major | Minor | Full target Achieved | -13 | -19
Strategic Focus 1: Increase capacity of LGUs to improve the delivery of social protection and social welfare services
DISASTER RESPONS AND MANAGEMENT PROGRAM
Outcome Indicators
3.1 | Percentage of disaster-affected households assisted to early recovery stage | ANA | ANA | ANA | ANA | ANA | 100% (15,077) |  | 100% (15,077) |  |  |  | 100% (15,077) | 0% |  |  | / |  | The field office adhered to the request of LGUs for augmentation support in response to the effect of a declaration of lockdowns and enhanced community quarantine due to the COVID-19 pandemic. Moreover, the families affected by the flooding due to sheerline and armed conflict were also given assistance to early recovery.
Output Indicators
3.1 | Number of trained DSWD QRT members ready for deployment on disaster response | 37 | 171 | 60 |  | 268 | 36 |  | 36 |  |  | 0 | 36 | -232 |  | / |  | One (1) participant from MAT Palanan, Isabela was not able to travel to Tuguegarao City due to bad weather conditions in Palanan. | The division was able to conduct Camp Coordination and Camp Management for IDP Protection for 36 DSWD staff. Close coordination with the participants was made by the training focal. Participants were asked to register at an earlier time and confirm their attendance to the training.
3.3 | Number of poor households that received cash-for-work for CCAM |  |  | 12650 | 17920 | 30570 |  |  | 0 |  |  | 0 | 0 | 30570 |  |  |  |  | Administered meetings and social preparation with Provincial Local Government Units on the conduct of Climate Change Adaptation and Mitigation as the main proponent of the activities to be conducted in selected Cities/Municipalities in their respective province. Implementation will begin in the 2nd semester of CY 2022 due to election ban.
3.4 | Number of LGUs provided with augmention on disaster response services | ANA |  |  |  | ANA | 20 |  | 20 |  |  | 0 | 20 |  |  |  | / |  | Due to the ongoing COVID-19 pandemic, the field office adhered to the request of LGUs and has provided Family Foods packs (FFPs) and Non-Food Items (NFIs) such as hygiene kits, sleeping kits, and modular tents to the municipalities that have declared Enhanced Community Quarantine (ECQ) and calibrated lockdowns. 20 LGUs who requested augmentation support were provided with assistance. Moreover, the FO also provided the following augmentation requests: - CONG. LUISA LLOREN CUARESMA for 10000 FFPs (amounting to 774,900) for the municipality of Bambang, Nueva Vizcaya.
3.5 | Number of internally displaced households provided with disaster response services | ANA |  |  |  | ANA | 242 |  | 242 |  |  | 0 | 242 | 242 |  |  | / |  | There are 172 displaced families were caused by flooding in Claveria, Cagayan, and 113 displaced families were caused by armed conflict in Sta. Teresita and Gonzaga, Cagayan. They were provided with disaster response services such as evacuation centers for IDPs, FFPs, hygiene, and sleeping.
3.6 | Cash for Work | 5561 |  |  |  | 5561 | 5224 |  | 5224 |  |  | 0 | 5224 | -337 |  | /
| Partially Damage | 2074 |  |  |  | 2074 | 2009 |  | 2009 |  |  | 0 | 2009 | -65 |  | / |  | The reported number of damaged houses is greater than the actual validated damaged houses. The total unpaid amount for ESA and CFW for affected families with damaged houses is Php 926,150.00. Php 450,000.00 was already returned to the Bureau of Treasury. The remaining Php 476,150.00 is still in the process to be returned to the Bureau of Treasury. | * Continuing fund from AY 2021 for TY KIKO 2009 out of 2074 (96.87%) beneficiaries with totally damaged houses due to TY KIKO was provided with CFW.
| Totally Damage | 267 |  |  |  | 267 | 260 |  | 260 |  |  | 0 | 260 | -7 |  | / |  |  | * Continuing fund from AY 2021 for TY KIKO 260 out of 267 (97.38%) beneficiaries with totally damaged houses due to TY KIKO was provided with CFW.
| Cash for Work for Community Works | 3220 |  |  |  | 3220 | 2955 |  | 2955 |  |  | 0 | 2955 | -265 |  | / |  | The reported number of damaged houses is greater than the actual validated damaged houses. The total unpaid amount for CFW for Community Work is Php 1,470,750.00. It was already returned to the Bureau of Treasury | * Continuing fund from AY 2021 for TY KIKO 2,955 out of 3,220 (91.77%) beneficiaries with partially damaged houses due to TY KIKO (Batanes) were provided with CFW for community work.
3.7 | Food for Work for Community Works | ANA |  |  |  | ANA | 2220 |  | 2220 |  |  | 0 | 2220 |  |  |  | / |  | 2100 FFPs were given to the province of Batanes for their Food-for-Work activities Basco - Clearing of creeks and tourist spots & Coastal Cleanup Itbayat - Tree Planting & Coastal Cleanup Ivana - Coastal Cleanup Mahatao - Coastal Cleanup Sabtang - Tree Planting Uyugan - Coastal Cleanup
3.8 | Emergency Shelter Assistance | 1418 |  |  |  | 1418 | 1350 |  | 1350 |  |  | 0 | 1350 | -68
| Partially Damage | 1247 |  |  |  | 1247 | 1184 |  | 1184 |  |  | 0 | 1184 | -63 |  | / |  | The reported number of damaged houses is greater than the actual validated damaged houses. The total unpaid amount for ESA and CFW for affected families with damaged houses is Php 926,150.00. Php 450,000.00 was already returned to the Bureau of Treasury. The remaining Php 476,150.00 is still in the process to be returned to the Bureau of Treasury. | * Continuing fund from AY 2021 for TY KIKO 1,184 out of 1,247 (94.95%) beneficiaries with partially damaged houses due to TY KIKO (Batanes) were provided with ESA.
| Totally Damage | 171 |  |  |  | 171 | 166 |  | 166 |  |  | 0 | 166 | -5 |  | / |  |  | * Continuing fund from AY 2021 for TY KIKO 166 out of 171 (97.08%) beneficiaries with totally damaged houses due to TY KIKO (Batanes) were provided with ESA.
3.9 | Percentage compliance to the mandated stockpile |  |  |  |  | 100% | 142.89% (28,578) |  | 142.89% (28,578) |  |  |  | 142.89% (28,578) |  |  |  | / |  | Ongoing and continuous production of FFPs
| Submitted by: |  |  |  | Reviewed by: | [9 empty] | Recommending Approval: |  |  |  | Approved by:
| REYMART P. CUSIPAG |  |  |  | DULCENEAH LYRA F. DELA CRUZ | [9 empty] | CHANDA T. API |  |  |  | CEZARIO JOEL C. ESPEJO
| Planning Officer 1 |  |  |  | Head, Policy Development and Planning Section (PDPS) | [9 empty] | SWO IV/OIC Chief, PPD |  |  |  | Regional Director

## OO3 FINANCIAL
DEPARTMENT OF SOCIAL WELFARE AND DEVELOPMENT
FIRST QUARTER ACCOMPLISHMENT REPORT
FY 2021
Objective/ Program/ Sub-Program/ Performance Indicator | Budget (GAA) | OBLIGATION | [9 empty] | DISBURSEMENT
|  | Amount |  |  |  |  | Percent Utilization |  |  |  |  | Amount |  |  |  |  | Percent Utilization
|  | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
Strategic Focus 1: Increase capacity of LGUs to improve the delivery of social protection and social welfare services
ORGANIZATIONAL OUTCOME 3: IMMEDIATE RELIEF AND EARLY RECOVERY OF DISASTERVICTIMS/SURVIVORS ENSURED
DISASTER RESPONSE AND MANAGEMENT PROGRAM
Grand Total | 62043300 | 10942489.5 | 0 | 0 | 0 | 10942489.5 | 100% | 0% | 0% | 0% | 100% | 10942489.5 | 0 | 0 | 0 | 131934407.7 | 100% | 0% | 0% | 0% | 100%
Disaster Response and Rehabilitation Program - Climate Change
Cash for Work (CFW) for Community Works on Climate Change Adaptation and Mitigation (CCAM) | 113109000 |  |  |  |  | 0 | 0% |  |  |  | 0% | 0 |  |  |  | 0 | 0% |  |  |  | 0%
Quick Response Fund - (2021 Continuing Fund)
Family Food Pack | ANA | 8833279.45 |  |  |  | 8833279.45 | 100% |  |  |  | 100% | 8833279.45 |  |  |  | 8833279.45 | 100% |  |  |  | 100%
Non Food Items | ANA | 963570.05 |  |  |  | 963570.05 | 100% |  |  |  | 100% | 963570.05 |  |  |  | 963570.05 | 100% |  |  |  | 100%
Food For Work | ANA | 1145640 |  |  |  | 1145640 | 100% |  |  |  | 100% | 1145640 |  |  |  | 1145640 | 100% |  |  |  | 100%
Quick Response Fund - Calamity Fund (Continuing Fund)
CFW
Totally | 5130000 | 5130000 |  |  |  | 5130000 | 100% |  |  |  | 100% | 4980000 |  |  |  | 4980000 | 97.08% |  |  |  | 97.08%
Partially | 12470000 | 12470000 |  |  |  | 12470000 | 100% |  |  |  | 100% | 11840000 |  |  |  | 11840000 | 94.95% |  |  |  | 94.95%
ESA
Totally | 987900 | 987900 |  |  |  | 987900 | 100% |  |  |  | 100% | 962000 |  |  |  | 962000 | 97.38% |  |  |  | 97.38%
Partially | 3836900 | 3836900 |  |  |  | 3836900 | 100% |  |  |  | 100% | 3716650 |  |  |  | 3716650 | 96.87% |  |  |  | 96.87%
Submitted by: | [6 empty] | Reviewed by: | [5 empty] | Recommending Approval: | [5 empty] | Approved by:
REYMART P. CUSIPAG | [6 empty] | DULCENEAH LYRA F. DELA CRUZ | [5 empty] | CHANDA T. API | [5 empty] | CEZARIO JOEL C. ESPEJO
Planning Officer 1 | [6 empty] | Head, Policy Development and Planning Section (PDPS) | [5 empty] | SWO IV/OIC Chief, PPD | [5 empty] | Regional Director

## OO4 PHYSICAL
DEPARTMENT OF SOCIAL WELFARE AND DEVELOPMENT
FIRST QUARTERLY ACCOMPLISHMENT REPORT
FY 2022
Strategy/ Program/ Sub-Program/ Performance Indicator |  | Physical Targets | [6 empty] | Physical Accomplishments | [6 empty] | Variance | Assessment of Variance |  |  | Reasons for Variance | Steering Measures
|  | Q1 | Q2 | 1st sem | Q3 | Q4 | 2nd sem | Total | Q1 | Q2 | 1st Sem | Q3 | Q4 | 2nd Sem | Total
[17 empty] | Major | Minor | Full target Achieved
Strategic Focus 2: Improve well-being of Beneficiaries and 4Ps households through strengthened social welfare system
ORGANIZATIONAL OUTCOME 4: CONTINUING COMPLIANCE OF SOCIAL WELFARE AND DEVELOPMENT AGENCIES TO STANDARDS IN THE DELIVERY OF SOCIAL WELFARE SERVICES ENSURED
Outcome Indicators
1 | Percentage of complaints received by the Field Office against erring SWDAs | ANA | ANA | ANA | ANA | ANA | ANA | ANA | [11 empty] | There were no complaints received by the Field Office against erring SWDAs. | Strengthen the advocacy activities of the Standards Section on regulatory services and standard guidelines as well as to ensure compliance of SWDAs to the set standards through monitoring visit.
2 | Percentage of SWDAs with sustained compliance to SWD Standards
2.1 | Private SWDAs with valid RL (operational within the region only) |  | 3 | 3 |  | 3 | 3 | 6 | [12 empty] | The Standards Section has already forwarded communication letters to SWDAs with valid R/L for the conduct of monitoring visit, also the section has already set its schedule for the said visit.
2.2 | LGU-managed SWDAs with valid Accreditation (operational within the region only) | 1 | 4 | 5 | 2 | 1 | 3 | 8 | 1 |  | 1 |  |  |  | 1 |  |  |  | / | Accomplishment achieved the target | The Standards Section has already forwarded communication letters to LGU-managed SWDAs with valid Accreditation for the conduct of monitoring visit, also the section has already set its schedule for the said visit.
2.3 | DSWD-managed SWDAs with valid Accreditation (operational within the region only) |  | 1 | 1 | 1 | 1 | 2 | 3 | [12 empty] | The Standards Section is strengthening its participation/membership to the Regional Inspectorate Committee, also the section has already set its schedule for monitoring visit.
Output Indicators
3 | Number of SWDAs registered and licensed
3.1 | Registered SWDAs | [7 empty] | 1 |  | 1 |  |  |  | 1 | [5 empty] | These indicators are merged/combined per 2022 NEP/GAA, shared/forwarded by the Standards Bureau on March 14, 2022.
3.2 | Licensed SWDAs | 1 | 1 | 2 | 1 |  | 1 | 3 | 3 |  | 3 |  |  |  | 3 |  |  |  | / | Accomplishment exceeded the target
4 | Beneficiary CSO Accredited | ANA | ANA | ANA | ANA | ANA | ANA | ANA | [11 empty] | There were no applicants.
5 | Number of service providers accredited
5.1 | Pre-Marriage Counselor | 2 | 3 | 5 | 5 | 3 | 8 | 13 | 2 |  | 2 |  |  |  | 2 |  |  |  |  | Accomplishment achieved the target
5.2 | DCWs(ECCD Services) | 50 | 130 | 180 | 167 | 60 | 227 | 407 | 31 |  | 31 |  |  |  | 31 |  |  | / |  | Limited request of LGUs for the conduct of external recognition assessment, also some of the child development centers are still in the process of internal recognition assessment. | Strengthen the advocay activity of the Standards Section through the conduct of orientation on the new ECCD Guidelines/Tool for Registration and Granting of Permit and Recognition to public and private child development centers and learning centers in their respective LGUs.
Remarks: Majority of the indicators are the core functions of the Standard Bureau, which are not applicable to the FO. Hence, these indicators have been simplified to have with the core functions of FO -SS.
| Submitted by: | [6 empty] | Reviewed by: | [10 empty] | Recommending Approval: |  | Approved by:
| REYMART P. CUSIPAG | [6 empty] | DULCENEAH LYRA F. DELA CRUZ | [10 empty] | CHANDA T. API |  | CEZARIO JOEL C. ESPEJO
| Planning Officer 1 | [6 empty] | Head, Policy Development and Planning Section (PDPS) | [10 empty] | SWO IV/OIC Chief, PPD |  | Regional Director

## OO4 FINANCIAL
DEPARTMENT OF SOCIAL WELFARE AND DEVELOPMENT
FIRST QUARTERLY ACCOMPLISHMENT REPORT
FY 2022
Strtegy/ Program/ Sub-Program/ Performance Indicator | Budget (GAA) | OBLIGATION | [9 empty] | DISBURSEMENT
|  | Amount |  |  |  |  | Percent Utilization |  |  |  |  | Amount |  |  |  |  | Percent Utilization
|  | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
Strategic Focus 2: Improve well-being of Beneficiaries and 4Ps households through strengthened social welfare system
ORGANIZATIONAL OUTCOME 4: CONTINUING COMPLIANCE OF SOCIAL WELFARE AND DEVELOPMENT AGENCIES TO STANDARDS IN THE DELIVERY OF SOCIAL WELFARE SERVICES ENSURED
Regulatory Services
SOCIAL WELFARE AND DEVELOPMENT AGENCIES REGULATORY PROGRAM
MOOE (Current Fund)
Supplies | 19575 | 19575 |  |  |  | 19575 | 100% |  |  |  | 100% | 0 |  |  |  | - | 0%
Traveling Expenses | 71875 | 16165 |  |  |  | 16165 | 22.49% |  |  |  | 22.49% | 16165 |  |  |  | 16165 | 100%
Training and Schoalrship Expenses | 53000 | 0 |  |  |  | 0 | 0% |  |  |  | 0% | 0 |  |  |  | 0 | 0%
Professional Services | 315180 | 117715.37 |  |  |  | 117715.37 | 37.35% |  |  |  | 37.35% | 84273.64 |  |  |  | 84273.64 | 71.59%
Financial Assistance/Subsidy | 210000 | 0 |  |  |  | 0 | 0% |  |  |  | 0% | 0 |  |  |  | 0 | 0%
Rents-Motor vehicles | 125000 | 0 |  |  |  | 0 | 0% |  |  |  | 0% | 0 |  |  |  | 0 | 0%
MOOE (Continiung Fund) | [10 empty] | 0%
Traveling Expenses | 8650 | 900 |  |  |  | 900 | 10.4% |  |  |  | 10.4% | 900 |  |  |  | 900 | 100%
Training and Schoalrship Expenses | 81618.91 | 50000 |  |  |  | 50000 | 61.26% |  |  |  | 61.26% | 50000 |  |  |  | 50000 | 100%
Financial Assistance/Subsidy | 104500 | 6500 |  |  |  | 6500 | 6.22% |  |  |  | 6.22% | 6500 |  |  |  | 6500 | 100%
Professional Services | 34875.27 | 34875.27 |  |  |  | 34875.27 | 100% |  |  |  | 100% | 0 |  |  |  | 0 | 0%
Rents-Motor vehicles | 116928.61 | 0 |  |  |  | 0 | 0% |  |  |  | 0% | 0 |  |  |  | 0 | 0%
| Submitted by: |  |  |  |  | Reviewed by: | [6 empty] | Recommending Approval: |  |  |  |  | Approved by:
| REYMART P. CUSIPAG |  |  |  |  | DULCENEAH LYRA F. DELA CRUZ | [6 empty] | CHANDA T. API |  |  |  |  | CEZARIO JOEL C. ESPEJO
| Planning Officer 1 |  |  |  |  | Head, Policy Development and Planning Section (PDPS) | [6 empty] | SWO IV/OIC Chief, PPD |  |  |  |  | Regional Director

## OO5 PHYSICAL
HPMES Form 4B
DEPARTMENT OF SOCIAL WELFARE AND DEVELOPMENT
FIRST QUARTERLY ACCOMPLISHMENT REPORT
FY 2022
Strategy/ Program/ Sub-Program/ Performance Indicator |  | Physical Targets |  |  |  |  | Physical Accomplishments | [5 empty] | Variance | Assessment of Variance |  |  | Reasons for Variance/ Other Remarks | Steering Measures
|  | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 |  | Total |  | Major | Minor | Full target Achieved
-1 |  | -2 | -3 | -4 | -5 | -6 | -7 | -8 | -9 | -10 |  | (11)=(7)+(8)+(9)+(10) | (12)=(11)-(6) |  |  |  | -13 | -19
Strategic Focus 1: Increase capacity of LGUs to improve the delivery of social protection and social welfare services
ORGANIZATIONAL OUTCOME 5: DELIVERY OF SOCIAL WELFARE AND DEVELOPMENT PROGRAMS BY LOCAL GOVERNMENT UNITS THROUGH LOCAL SOCIAL WELFARE AND DEVELOPMENT OFFICES IMPROVED
Outcome
5.1 | Percentage of LSWDOs with improved functionality | 0% | 22% (10 LGUs) | 78% (35 LGUs) |  | 100% (45 LGUs) | [11 empty] | As per SWIDB's advance memo, target schedule of the Service Delivery Capacity Assessment to LGUs/LSWDOs is on June-August 2022. Thus, earlier target schedules are to be postponed in conformity with the said memo. This will also facilitate and contribute to enough time of preparation of the LGUs/LSWDOs on the necessary documents needed for the assessment.
Baseline Result:
Re-assessment on the Service Delivery Capacity based on the results of assessment to LGUs/LSWDOs on CY 2019 & CY 2020. | [16 empty] | Target LGUs/LSWDOs for assessment during the first quarter was unable to push through for the election period and there'll be new sets of LCEs by then. Further, as per advance Memo from the SWIDB, Service Delivery Re-Assessment (SDCA) is scheduled on the 2nd and 3rd quarters after the scheduled orientation on May 18, 2022 by the Bureau.
a. Level 1 |  | See remarks
a.1 Province
a.2 City
| a.3 Municipality | 19
b. Level 2 |  | See remarks
| b.1 Province | 3
| b.2 City | 1
| b.3 Municipality | 21
c. Level 3 |  | See remarks
| c.1 Province | 2
| c.2 City | 3
| c.3 Municipality | 7
d. Low or Below Level 1 |  | See remarks
c.1 Province
c.2 City
| c.3 Municipality | 1
Re-assessment on the Service Delivery Compentency based on the results of assessment to LGUs/LSWDOs on CY 2019 & CY 2020: | [16 empty] | Target LGUs/LSWDOs for assessment during the first quarter was unable to push through for the election period and there'll be new sets of LCEs by then. Further, as per advance Memo from the SWIDB, Service Delivery Re-Assessment (SDCA) is scheduled on the 2nd and 3rd quarters after the scheduled orientation on May 18, 2022 by the Bureau. SDCA and Competency Needs Assessment (CNA) are combined by the SWDB-CO known as Service Delivery Capacity and Competency Assessment (SDCCA).
Expert Competency |  | See remarks
a.1 Province
a.2 City
a.3 Municipality
Expert Competency |  | See remarks
b.1 Province
b.2 City
b.3 Municipality
Intermediate Competency |  | See remarks
c.1 Province
c.2 City
c.3 Municipality
Basic |  | See remarks
c.1 Province
c.2 City
c.3 Municipality
Output Indicators
5.1 | Number of LGUs provided with LDI | 0 | 20 | 40 |  | 60 | [10 empty] | Conduct of LDI Batch 1 based on the approved IDCB Plan is June 2022. For the quarter, preparation for the conduct of the LDI has been done e.g. crafting of Training Design, proposal and other requirements for PRC accrediation.
5.2 | Number of LGUs assess in terms of their functionality level along delivery of social protection | 0 | 10 | 35 |  | 45 | [11 empty] | As per SWIDB's advance memo, target schedule of the Service Delivery Capacity Assessment to LGUs/LSWDOs is on June-August 2022. Thus, earlier target schedules are to be postponed in conformity with the said memo. This will also facilitate and contribute to enough time of preparation of the LGUs/LSWDOs on the necessary documents needed for the assessment.
5.3 | Percentage of LGUs provided with technical assistance | Annual Targeting | Annual Targeting | Annual Targeting | Annual Targeting | 85% to 100% of 57 LGUs or 48 to 57 LGUs | 17.54% (10 LGUs) |  |  |  |  | 17.54% (10 LGUs) | -47 | / |  |  | Technical assistance is being provided as per the LGUs request and planned activities for further technical assistance provision are to be conducted starting April 2022 onwards. One of the basis of the activities to be conducted is the result of the 2019-2021 Service Delivery Capacity Assessment as per indicated during the exit conference on the findings and recommendations made by the Regional Monitoring Team (RMT) members | The different Offices of the Field Office were able to respond on concerns of some LGUs/LSWDOs like the need for Orientation on the New EECD Guidelines, Adoption concerns, Child Labor Local Registry System, Child at Risk, Children in Conflict with the Law and assisted in the LGU's compliance on Social Welfare and Development Law Monitoring Report
5.5 | Percentage of LGUs provided with resource augmentation | 100% | 100% | 100% | 100% | 100% | 100% (20 LGUs) |  |  |  |  | 100% (20 LGUs) | 0 |  |  | / |  | Number of LGUs provided with augmention on disaster response services
5.6 | Percentage of LGUs that rated TA provided as satisfactory or better | 100% | 100% | 100% | 100% | 100% | 100% (10 LGUs) |  |  |  |  | 100% (10 LGUs) | 0 |  |  | /
5.7 | Percentage of LGUs that rated RA provided as satisfactory or better | 100% | 100% | 100% | 100% | 100% | 100% (20 LGUs) |  |  |  |  | 100% (20 LGUs) | 0 |  |  | /
| Submitted by: |  |  |  |  | Reviewed by: |  |  |  |  | Recommending Approval: |  |  | Approved by:
| REYMART P. CUSIPAG |  |  |  |  | DULCENEAH LYRA F. DELA CRUZ |  |  |  |  | CHANDA T. API |  |  | CEZARIO JOEL C. ESPEJO
| Planning Officer 1 |  |  |  |  | Head, Policy Development and Planning Section (PDPS) |  |  |  |  | SWO IV/OIC Chief, PPD |  |  | Regional Director

## OO5 FINANCIAL
DEPARTMENT OF SOCIAL WELFARE AND DEVELOPMENT
10
FY 2022
Strategy/ Program/ Sub-Program/ Performance Indicator | Budget (GAA) | OBLIGATION | [9 empty] | DISBURSEMENT
|  | Amount |  |  |  |  | Percent Utilization |  |  |  |  | Amount |  |  |  |  | Percent Utilization
|  | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total
Strategic Focus 1: Increase capacity of LGUs to improve the delivery of social protection and social welfare services
ORGANIZATIONAL OUTCOME 5: DELIVERY OF SOCIAL WELFARE AND DEVELOPMENT PROGRAMS BY LOCAL GOVERNMENT UNITS THROUGH LOCAL SOCIAL WELFARE AND DEVELOPMENT OFFICES IMPROVED
Provision of Technical/Advisory Assistance and Related Services
Total Approved TARA MOOE (Current Fund) | 10915000 | 2936331.14 |  |  |  | 2936331.14 | 26.9% |  |  |  | 26.9% | 244894.36 |  |  |  | 244894.36 | 8.34% |  |  |  | 8.34%
Total Approved TARA MOOE (Continuing Fund) | 1422091.24 | 631684.71 |  |  |  | 631684.71 | 44.42% |  |  |  | 44.42% | 194659.57 |  |  |  | 194659.57 | 30.82% |  |  |  | 30.82%
| Submitted by: |  |  |  | Reviewed by:
[13 empty] | Recommending Approval: |  |  |  |  | Approved by:
| REYMART P. CUSIPAG |  |  |  | DULCENEAH LYRA F. DELA CRUZ | [7 empty] | CHANDA T. API |  |  |  |  | CEZARIO JOEL C. ESPEJO
| Planning Officer 1 |  |  |  | Head, Policy Development and Planning Section (PDPS) | [7 empty] | SWO IV/OIC Chief, PPD |  |  |  |  | Regional Director

## STO PHYSICAL
DEPARTMENT OF SOCIAL WELFARE AND DEVELOPMENT
FIRST QUARTERLY ACCOMPLISHMENT REPORT
FY 2022
Strategy/ Program/ Sub-Program/ Performance Indicator |  |  |  | Physical Targets | [5 empty] | Accomplishment |  |  |  | Variance |  | Assessment of Variance |  | Reasons for Variance | Steering Measures
|  | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | 1st Semester | Q3 | Q4 | 2nd Semester | Total
[15 empty] | Major | Minor | Full target Achieved
Policy and Plan Development
1 | Number of agency policies approved and disseminated | ANA | ANA | ANA | ANA | ANA | 3 |  | 3 |  |  |  | 3 | 3 |  |  | Full target Achieved | Not Applicabe. Target is as need arise | Closely monitor the progress of policies approved and disseminated
2 | Number of agency plans formulated and disseminated
| a. Medium-term Plans | ANA | ANA | ANA | ANA | ANA | 1 |  | 1 |  |  |  | 1 | 1 |  |  | Full target Achieved | Not Applicabe. Target is as need arise
| b. Annual Plans | ANA | ANA | ANA | ANA | ANA | 2 |  | 2 |  |  |  | 2 | 2 |  |  | Full target Achieved | Not Applicabe. Target is as need arise
3 | Number of researches completed | ANA | ANA | ANA | ANA | ANA | 2 |  | 2 |  |  |  | 2 | 2 |  |  | Full target Achieved | Not Applicabe. Target is as need arise | Coordinate closely with the researchers to ensure completion of research activities
4 | Number of position papers prepared | ANA | ANA | ANA | ANA | ANA | 0 |  | 0 |  |  |  | 0 | 0 |  |  | Not applicable | Not Applicabe. Target is as need arise | Not Applicabe
Social Technology Development
6 | Number of social technologies formulated
7 | Number of new concepts of models of interventions responding to emerging needs
8 | Number of new designs formulated
9 | Number of models of intervention pilot tested
10 | Number of models of intervention evaluated
11 | Number of SWD programs and services enhanced
12 | Number of concepts on the enhancement of an existing program/service
13 | Number of designs of enhanced programs/services formulated
14 | Number of enhanced models pilot tested
15 | Number of enhanced models evaluated
16 | Percentage of intermediaries adopting completed social technologies
Total no. of intermediaries implemented/pilot-tested social technologies
No. of intermediaries adopting completed social technologies
17 | Number of intermediaries replicating completed social technologies | 1 | 2 | 2 |  | 5 | 1 |  | 1 |  |  |  | 1 | 0 |  |  | Full target Achieved | Entered agreement with Municipality of Dinapigue,Isabela for the replication of HCSSSC received on January 2022 | Continue strong partnership with the LGU particularly on institutionalizing completed Social Technologies
18 | Number of completed social technologies promoted | N/A |  |  |  | N/A
19 | Number of ST portfolio
20 | Percentage of LGUs reached through social marketing activities |  |  |  |  | 100% | 0% |  | 0% |  |  |  | 0% | -100% | Major |  |  | LGU priorities and activities affected the accomplishment of targets | Continue strong partnership with the LGU for the orientation on completed models of intervention
| Total no. of LGUs targeted |  |  |  |  | 54 | 54 |  | 54 |  |  |  | 54
| No. of LGUs reached through social marketing activities |  |  |  |  | 54 | 0 |  | 0 |  |  |  | 0
National Household Targeting System for Poverty Reduction
21 | No. of intermediaries utilizing Listahanan results for social welfare and development initiatives | ANA | ANA | ANA | ANA | ANA | 8 |  | 8 |  |  |  | 8 |  |  |  | Full target Achieved
| a. No.of request for statistical data granted | ANA | ANA | ANA | ANA | ANA | 1 |  | 1 |  |  |  | 1
| b. No. of request for name-matching granted | ANA | ANA | ANA | ANA | ANA | 7 |  | 7 |  |  |  | 7
22 | No. of households assessed to determine poverty status | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  | N/A | Not applicable |  |  |  | Not applicable
23 | No. of barangays with functional Barangay Verification Team (BVT) | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  | N/A | Not applicable |  |  |  | Not applicable
24 | No. of cities/municipalities with functional Local Verification Committee (LVC) | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  | N/A | Not applicable |  |  |  | Not applicable
25 | Percentage of grievances received during validation phase resolved | ANA | ANA | ANA | ANA | ANA | N/A |  | N/A |  |  |  | N/A | Not applicable |  |  |  | Not applicable
26 | Results of the Listahanan 3 assessment launched | 0 | 0 | 0 | 1 | 1 | 0 |  | 0 |  |  |  | 0 | Not applicable |  |  |  | The Results of the Listahanan 3 assessment will be launched by 3rd quarter
| Regional profile of the poor developed | 0 | 0 | 0 | 1 | 1 | 0 |  | 0 |  |  |  | 0 | Not applicable |  |  |  | The development of regional profile of the poor has the same timeline the launching of the results of assessment
Information and Communications Technology Management
27 | DSWD Enterprise Network with Uptime of 95 percent for FO
| Percentage uptime for Field Office - II | 95% | 95% | 95% | 95% | 95% | 98% |  | 98% |  |  |  | 98% |  |  |  | Full target achieved
| Number of DSWD Sub- Regional Sites connected to the DSWD Enterprise Network | 13 | 13 | 13 | 13 | 13 | 14 |  | 14 |  |  |  | 14 |  |  |  | Full target achieved
28 | Percentage/Number of Information Systems developed/enhanced and maintained
| Percentage of functional information systems deployed and maintained | 100% | 100% | 100% | 100% | 100% | 23.08% |  | 23.08% |  |  |  | 23.08% |  | Major |  |  |  | Clarify the indicator with Central Office
| Number of Information systems developed/enhanced in partnership with Business Owner | 3 | 6 | 6 | 6 | 6 | 3 |  | 3 |  |  |  | 3
| Number of information systems maintained thru interventions and corresponding technical assistance to business owner/users | 13 | 13 | 13 | 13 | 13 | 13 |  | 13 |  |  |  | 13
29 | Purposive data management for information sharing
| Percentage of mission critical databases managed and maintained | 100% | 100% | 100% | 100% | 100% | 20% |  | 20% |  |  |  | 20% |  | Major |  |  |  | Clarify the indicator with Central Office
| Number of DSWD databases supporting programs, projects and services managed and maintained | 5 | 6 | 6 | 6 | 6 | 5 |  | 5 |  |  |  | 5
| Number of for build-up and deployed databases | 1 | 3 | 2 | 0 | 6 | 1 |  | 1 |  |  |  | 1
30 | Percentage uptime of DSWD Enterprise Network (Infrastructure Management)
| Percentage Uptime of Local Servers and Storage | 95% | 95% | 95% | 95% | 95% | 99% |  | 99% |  |  |  | 99% |  |  |  | Full target achieved
| Percentage uptime of local datacenter/interim datacenter | 95% | 95% | 95% | 95% | 95% | 99% |  | 99% |  |  |  | 99% |  |  |  | Full target achieved
| Percentage uptime of Heating, ventilation, and Air Conditioning (HVAC) | 95% | 95% | 95% | 95% | 95% | 99% |  | 99% |  |  |  | 99% |  |  |  | Full target achieved
| Number of functional websites developed and maintained | 1 |  |  |  |  | 1 |  | 1 |  |  |  | 1 |  |  |  | Full target achieved
| Percentage uptime of local hosted websites | 95% | 95% | 95% | 95% | 95% | 99% |  | 99% |  |  |  | 99% |  |  |  | Full target achieved
31 | Digital identity and transactions secured.
31.1 | Percentage of information systems developed subjected to vulnerability assessment and patched accordingly |  |  |  |  | 100% | 100% |  | 100% |  |  |  | 100% |  |  |  | Full target achieved
| Number of Information Systems with vulnerability assessment and patched accordingly | 1 | ANA | ANA | ANA | ANA | 1 |  | 1 | [7 empty] | Full target achieved
31.2 | Percentage of end points secured | 100% | 100% | 100% | 100% | 100% | 323.9% |  | 323.9% |  |  |  | 323.9% |  |  |  | Full target achieved
| Number of endpoints protected by enterprise antivirus/antimalware | 238 | 238 | 238 | 238 | 238 | 771 |  | 771 |  |  |  | 771
| Number of endpoint licenses | 238 | 238 | 238 | 238 | 238 | 238 |  | 238 |  |  |  | 238
32 | Responsive ICT support services
32.1 | Percentage of Technical Assistance (TA) requests responded and resolved within the set Service Level Agreement (SLA)/timeline
| Total Percentage of TA responded and resolved within SLA of All Division | 100% | 100% | 100% | 100% | 100% | 95.33% |  | 95.33% |  |  |  | 95.33% |  |  | Minor
| Total Number of TA received | ANA | ANA | ANA | ANA | ANA | 364 |  | 364 |  |  |  | 364 |  |  |  | Full target achieved
| Total Number of TA responded and resolved within SLA | ANA | ANA | ANA | ANA | ANA | 347 |  | 347 |  |  |  | 347 |  |  |  | Full target achieved
32.2 | Number of Learning and Development Interventions on ICT Service Management conducted | 0 | 1 | 1 | 0 | 2 | 0 |  | 0 |  |  |  | 0 |  | Major |  |  | The activity will be conducted in the 2nd quarter
32.3 | Number of Users Trained on ICT applications, websites, solutions, tools and products | 0 | 30 | 30 | 0 | 60 | 0 |  | 0 |  |  |  | 0 |  | Major |  |  | The activity will be conducted in the 2nd quarter
33 | ICT systems, facilities and infrastructure put in place
33.1 | Number of new ICT systems, ICT equipment, facilities and infrastructure put in place
| Number of new facilities and infrastructure put in place | 1 | 1 | 1 | 1 | 4 | 2 |  | 2 |  |  |  | 2 |  |  |  | Full target achieved
| Number of ICT Equipment put in place | ANA | ANA | ANA | ANA | ANA | 36 |  | 36 |  |  |  | 36 |  |  |  | Full target achieved
Internal Audit
34 | Percentage of IAS audit recommendations complied with | N/A | 7 | 8 | 8 | 100% | 0% |  | 0% |  |  |  | 0% | 0% | Major |  |  | N/A. The 1st quarterly reporting for 2022 will be on June 2022
| No.of IAS Audit Recommendations | N/A | 7 | 8 | 8 | 23 | 0 |  | 0 |  |  |  | 0
| Total No.of Audit Recommendations Complied | N/A | 7 | 8 | 8 | 23 | 0 |  | 0 |  |  |  | 0
35 | Percentage of integrity management measures implemented | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  | N/A | Not Applicable |  |  |  | Not Applicable
| Total No.of Integrity Measures Identified | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  | N/A
| Total No.of Integrity Measures Implemented | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  | N/A
Social Marketing
36 | Percentage of respondents aware of at least 2 DSWD programs except 4Ps | 50% awareness of SWDAs, LGUs, NGAs and beneficiaries of atleast 2 DSWD programs except 4Ps |  |  |  | 50% awareness of SWDAs, LGUs, NGAs and beneficiaries of atleast 2 DSWD programs except 4Ps | Report will be generated after KAP survey administration until EO of December |  | Report will be generated after KAP survey administration until EO of December | - |  |  | Report will be generated after KAP survey administration until EO of December | 0 | Major
37 | Number of social marketing activities conducted
| a. Information caravans (Virtual/Online and Community-based on the Air (radio) conducted by EO December 2021) | 1 | 1 | 1 | 1 | 4 | 7 |  | 7 |  |  |  | 7 | 3 |  |  | Full target achieved
| b. Issuance of press releases | ANA | ANA | ANA | ANA | ANA | 32 |  | 32 |  |  |  | 32 | 32 |  |  | Full target achieved
| c. Communication campaigns (conducted by end of Decefmber 2021) | 1 | 1 | 1 | 1 | 4 | 4 |  | 4 |  |  |  | 4 | 0 |  |  | Full target achieved
| d. Number of IEC materials developed | ANA | ANA | ANA | ANA | ANA | 84 |  | 84 |  |  |  | 84 | 84 |  |  | Full target achieved
Knowledge Management
39 | Number of knowledge products on social welfare and development services developed | 0 | 0 | 0 | 1 | 1 | 0 |  | 0 |  |  |  | 0 | -1 | Major |  |  | Not applicable. The target will be accomlished until end of December 2022.
40 | Number of knowledge sharing sessions conducted | 1 | 1 | 1 | 1 | 4 | 5 |  | 5 |  |  |  | 5 | 1 |  |  | Full target achieved | Collaborative efforts with all the sections and divisions. The following were the Big Group KSS conducted: 1. Year-end National Community-Driven Development Program Additional Financing (NCDDP AF) Performance Review and Evaluation Workshop (PREW) cum Team Building; 2. Program Orientation with DSWD Internals; 3. SLP Strategic Planning on CY 2022 Implementation; 4. Orientation on the Terms of Refference Administration of Disaster Assistance Family Access Card (DAFAC); and 5. CY 2022 Regional Management Dovelopment Conference (RMDC).
| Consolidated by: |  |  |  |  | Reviewed by: |  |  |  |  | Recommending Approval by: | [5 empty] | Approved by:
| NESTOR P. ESQUERO |  |  |  |  | DUCENEAH LYRA F. DELA CRUZ |  |  |  |  | CHANDA T. API | [5 empty] | CEZARIO JOEL C. ESPEJO
| Planning Officer I |  |  |  |  | Planning Officer IV/ Head, Policy Development and Planning Section |  |  |  |  | SWO IV/ OIC- Policy and Plans Division | [5 empty] | Regional Director
Note on E21: ====== ID#AAAAS91UBxA (2021-12-15 08:42:26) Done na po ang soc tech. pakireview po. thank you. -Constancia M Domingo

## GASS PHYSICAL
DEPARTMENT OF SOCIAL WELFARE AND DEVELOPMENT
FIRST QUARTERLY ACCOMPLISHMENT REPORT
FY 2022
Objective/ Program/ Sub-Program/ Performance Indicator |  | Physical Targets |  |  |  |  | PHYSICAL ACCOMPLISHMENT | [6 empty] | Variance | Reasons for Variance | Assessment of Variance |  |  | Steering Measures
|  | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | 1st Semester | Q3 | Q4 | 2nd Semester | Total
-1 |  | -2 | -3 | -4 | -5 | -6 | [6 empty] | (11)=(12)+(13)+(14)+(15) | (12)=(11)-(6) | -13 | Major | Minor | Full target Achieved | -19
GENERAL ADMINISTRATION AND SUPPORT SERVICES
Human Resource and Development
1 | Percentage of positions filled-up | 100% |  |  |  | 100% | 119% |  | 119% |  |  |  | 119% | 19.05% | Vacancies during the quarter were also filled up immediately. |  |  | Full target Achieved
| No. of Positions Filled up | 21 |  |  |  | 21 | 25 |  | 25 |  |  |  | 25
| Male | n/a |  |  |  |  | 5 |  | 5 |  |  |  | 5
| Female | n/a |  |  |  |  | 20 |  | 20 |  |  |  | 20
| Total no. of Positions with Request for Posting( As of Dec. 31, 2020) | 21 |  |  |  | 21 | 21 |  | 21 |  |  |  | 21
| Male | n/a
| Female | n/a
2 | Percentage of regular staff provided with at least 1 learning and development intervention | 24.49% | 24.49% | 25.51% | 25.51% | 100% | 45.92% |  | 45.92% |  |  |  | 45.92% | 21.43% |  |  |  | Full target Achieved
| No.of Staff Provided with Learning and Development Interventions | 24 | 24 | 25 | 25 | 98 | 45 |  | 45 |  |  |  | 45
| Male | 8 | 8 | 9 | 9 | 34 | 14 |  | 14 |  |  |  | 14
| Female | 16 | 16 | 16 | 16 | 64 | 31 |  | 31 |  |  |  | 31
| Total No. of Regular Staff | 98 | 98 | 98 | 98 | 98 | 98 |  | 98 |  |  |  | 98
Male
Female
3 | Number of personnel that attended at least one learning and development intervention | 865 |  |  |  | 865 | 0 |  | 0 |  |  |  | 0 | -865 |  | Major
| Digitization | 865 |  |  |  | 865 | 0 |  | 0 |  |  |  | 0
| Male | 275 |  |  |  | 275
| Female | 590 |  |  |  | 590
| Occupational health safety protocols | 865 |  |  |  | 865 | 0 |  | 0 |  |  |  | 0
| Male | 275 |  |  |  | 275
| Female | 590 |  |  |  | 590
4 | Number of personnel infected with COVID 19 regardless of work arrangement and employment status Department-wide |  |  |  |  | ANA | 118 |  | 118 |  |  |  | 118 | 118 | Not applicable. Indicator is As need arise |  |  | Full target achieved
| Male |  |  |  |  | ANA | 49 |  | 49 |  |  |  | 49
| Female |  |  |  |  | ANA | 69 |  | 69 |  |  |  | 69
5 | Number of personnel regardless of status provided with support and assistance |  |  |  |  | ANA | 1 |  | 1 |  |  |  | 1 | 1 | Only severe cases and hospitalized were catered |  |  | Full target achieved
| Infected Personnel |  |  |  |  | ANA | 1 |  | 1 |  |  |  | 1
| Male | ana |  |  |  | ANA | 1 |  | 1 |  |  |  | 1
| Female | ana |  |  |  | ANA | 0 |  | 0 |  |  |  | 0
| Bereaved Personnel | [5 empty] | 0 |  | 0 |  |  |  | 0
| Male | 0 |  |  |  |  | 0 |  | 0 |  |  |  | 0
| Female | 0 |  |  |  |  | 0 |  | 0 |  |  |  | 0
6 | Percentage of staff provided with compensation/benefits within timeline |  |  |  |  | 100% | 100% |  | 100% |  |  |  | 100% | 0% |  |  |  | Full target achieved
| Total No. of staff |  |  |  |  | 1069 | 1069 |  | 1069 |  |  |  | 1069
| Male |  |  |  |  | 315 | 315 |  | 315 |  |  |  | 315
| Female |  |  |  |  | 754 | 754 |  | 754 |  |  |  | 754
| No.of Staff Receiving Salary and Benefits on Time |  |  |  |  | 1069 | 1069 |  | 1069 |  |  |  | 1069
| Male |  |  |  |  | 315 | 315 |  | 315 |  |  |  | 315
| Female |  |  |  |  | 754 | 754 |  | 754 |  |  |  | 754
Legal Services ( Atty. III was hired on September 20, 2021 and Legal Assistant was hired on October 18, 2021)
7 | Percentage of disciplinary cases resolved within timeline |  |  |  |  | ANA | 0% |  | 0% |  |  |  | 0% |  | Not applicable. Indicator is As need Arises
| Total No.of Disciplinary Cases Resolved within Timeline |  |  |  |  | ANA | 0 |  | 0 |  |  |  | 0
| 7.4.1 Number of disciplinary cases initiated |  |  |  |  | ANA | 0 |  | 0 |  |  |  | 0
| 7.4.2 Number of complaints resolved |  |  |  |  | ANA | 0 |  | 0 |  |  |  | 0
8 | Percentage of litigated cases resolved in favor of the Department or Department Personnel |  |  |  |  | ANA | 100% |  | 100% |  |  |  | 100% | 100% | Not applicable. Indicator is As need Arises |  |  | Full target achieved
| No. of Litigated Cases Resolved with Favorable Outcome |  |  |  |  | ANA | 1 |  | 1 |  |  |  | 1 | 1
| Total No.of Litigated Cases Resolved |  |  |  |  | ANA | 1 |  | 1 |  |  |  | 1 | 1
| 7.5.1 Number of hearings attended |  |  |  |  | ANA | 2 |  | 2 |  |  |  | 2 | 2
| 7.5.2 Number of preliminmary investigations and/or case conferences attended |  |  |  |  | ANA | 1 |  | 1 |  |  |  | 1 | 1
9 | Percentage of requests for legal assistance addressed |  |  |  |  | ANA | 100% |  | 100% |  |  |  | 100% | 100% | Not applicable. Indicator is As need Arises
| No. of Legal Assistance Requests Addressed |  |  |  |  | ANA | 257 |  | 257 |  |  |  | 257 | 257
| Total No.of Legal Assistance Requests |  |  |  |  | ANA | 257 |  | 257 |  |  |  | 257 | 257
| 7.6.1 Number of written legal opinions provided |  |  |  |  | ANA | 2 |  | 2 |  |  |  | 2 | 2
| 7.6.2 Number of TAs provided to clients |  |  |  |  | ANA | 255 |  | 255 |  |  |  | 255 | 255
Administrative Services
10 | Number of facilities repaired/renovated |  |  |  |  | 19 | 19 |  | 19 |  |  |  | 19 | 0 |  |  |  | Full target Achieved
11 | Percentage of real properties titled |  |  |  |  | 100% | 100% |  | 100% |  |  |  | 100% | 0% |  |  |  | Full target Achieved
| No.of Real Properties with Title |  |  |  |  | 4 | 4 |  | 4 |  |  |  | 4
| Total No.of DSWD-owned Real Properties |  |  |  |  | 4 | 4 |  | 4 |  |  |  | 4
12 | Number of vehicles maintained and managed |  |  |  |  | 16 | 16 |  | 16 |  |  |  | 16 |  |  |  |  | Full target Achieved
13 | Percentage of records digitized/disposed
| Percentage of records digitized | 100% |  |  |  | 100% | 100% |  | 100% |  |  |  | 100% |  | Not applicable. Covers digitized/scanned RSOs, Travel Orders, Memo, directives from the Regional Director and other issuances |  |  | Full target Achieved
| Number of records digitized | 1281 |  |  |  | 1281 | 1281 |  | 1281 |  |  |  | 1281
| Number of records identified for digitization | 1281 |  |  |  | 1281 | 1281 |  | 1281 |  |  |  | 1281
| Percentage of records disposed | 100% |  |  |  | 100% | 0% |  | 0% |  |  |  | 0% | -100% | Approval of the 2021 Request for Authority to Dispose Valueless Records was received on March 31, 222 . NAP has not identified any schedule for disposal yet. | Major
| Number of records disposed | 41 |  |  |  | 41 | 0 |  | 0 |  |  |  | 0
| Number of records identified for disposal | 41 |  |  |  | 41 | 41 |  | 41 |  |  |  | 41
Financial Management
14 | Percentage of budget utilized
| a. Actual Obligations Over Actual Allotment Incurred | 25% |  |  |  | 100% | 23.32% |  | 23.32% |  |  |  | 23.32% |  | As of April 7, 2022. |  | Minor
| Total Actual Obligation Incurred | [5 empty] | 837793223.18 |  | 837793223.18 |  |  |  | 837793223.18
| Total Actual Annual Allotment Received | [5 empty] | 3592636445.34 |  | 3592636445.34 |  |  |  | 3592636445.34
| b. Actual Disbursements over Actual Obligations Incurred |  |  |  |  | 100% | 87.83% |  | 87.83% |  |  |  | 87.83% |  |  |  |  | Full target Achieved
| Total Actual Disbursement | [5 empty] | 735872968.61 |  | 735872968.61 |  |  |  | 735872968.61
| Total Actual Annual Obligation Incurred | [5 empty] | 837793223.18 |  | 837793223.18 |  |  |  | 837793223.18
15 | Percentage of cash advance liquidated
| a. Advances to officers and employees |  |  |  |  | 100% | 19.07% |  | 19.07% |  |  |  | 19.07% |  | As of April 7, 2022. |  | Minor
| Total Amount Liquidated | [5 empty] | 182761.24 |  | 182761.24 |  |  |  | 182761.24
| Total Cash Advance Processed | [5 empty] | 958402.64 |  | 958402.64 |  |  |  | 958402.64
| b. Advances to SDOs | [16 empty] | Full target Achieved
| b.1 Current Year |  |  |  |  | 100% | 46.61% |  | 46.61% |  |  |  | 46.61%
| Total Amount Liquidated | [5 empty] | 337354888.24 |  | 337354888.24 |  |  |  | 337354888.24
| Total Cash Advance Processed | [5 empty] | 723840797 |  | 723840797 |  |  |  | 723840797
| b.2 Prior Years | [5 empty] | 76.74% |  | 76.74% |  |  |  | 76.74%
| Total Amount Liquidated | [5 empty] | 270396206.68 |  | 270396206.68 |  |  |  | 270396206.68
| Total Cash Advance Processed | [5 empty] | 352365647.42 |  | 352365647.42 |  |  |  | 352365647.42
c. Inter-agency transferred funds
| c.1 Current Year |  |  |  |  | 100% | 0% |  | 0% |  |  |  | 0% |  | As of April 7, 2022. | Major
| Total Amount Liquidated | [5 empty] | 0 |  | 0 |  |  |  | 0
| Total Cash fund transferred | [5 empty] | 58498600.08 |  | 58498600.08 |  |  |  | 58498600.08
| c.2 Prior Years |  |  |  |  | 100% | 39.86% |  | 39.86% |  |  |  | 39.86% |  | As of April 7, 2022. |  | Minor
| Total Amount Liquidated | [5 empty] | 90236354.09 |  | 90236354.09 |  |  |  | 90236354.09
| Total Cash fund transferred | [5 empty] | 226408841.06 |  | 226408841.06 |  |  |  | 226408841.06
16 | Percentage of AOM responded within timeline |  |  |  |  | ANA | 100% |  | 100% |  |  |  | 100% |  |  |  |  | Full target Achieved
| No.of AOM Responded withinTimeline |  |  |  |  | ANA | 19 |  | 19 |  |  |  | 19
| Total No.of AOM Received |  |  |  |  | ANA | 19 |  | 19 |  |  |  | 19
17 | Percentage of NS/ND complied within timeline |  |  |  |  | ANA | 0% |  | 0% |  |  |  | 0% |  |  |  |  | Full target Achieved
| No. of Notice of Suspension/Notice of Disallowances Responded within Timeline |  |  |  |  | ANA | 0 |  | 0 |  |  |  | 0
| No. of Notice of Suspension/Notice of Disallowances Received |  |  |  |  | ANA | 0 |  | 0 |  |  |  | 0
Procurement Services
18 | Percentage of procurement projects completed in accordance with applicable rules and regulations |  |  |  |  | ANA | 25.91% |  | 25.91% |  |  |  | 25.91% | Not applicable. Target is as need arise | Imposition of lockdown affected movement of staff |  | Minor
| Total No.of PR Received |  |  |  |  | ANA | 521 |  | 521 |  |  |  | 521
| No.of PR Processes Awarded and Contracted on Time |  |  |  |  | ANA | 135 |  | 135 |  |  |  | 135
19 | Percentage compliance with reportorial requirements for oversight agencies |  |  |  |  | 100% | 100% |  | 100% |  |  |  | 100% |  |  |  |  | Full target achieved
| Total No.of Reports Required by Oversight Agencies |  |  |  |  | 2 | 2 |  | 2 |  |  |  | 2
| No.of Reports Required complied with |  |  |  |  | 2 | 2 |  | 2 |  |  |  | 2
Percentage of Technical Assistance provided to Central Office OBSUs and Field Offices relating to various procurement projects as requested and/or as initiated through Procurement Facilitation Meetings
Number of TAs provided
Total Number of TA request received
Number of innovative/good practices for organizational and process excellence
Percentage of capacity-building trainings/workshops conducted as planned
20 | Percentage of Central Office OBSUs and other procurement partners satisfied with the services rendered
Total No. of CO OBSUs and procurements partners satisfied with the services rendered
Total No. of CO OBSUs and procurements partners subjected for satisfaction survey
| Consolidated by: |  |  |  |  | Reviewed by: |  |  |  |  | Recommending Approval by: | [5 empty] | Approved by:
| NESTOR P. ESQUERO |  |  |  |  | DUCENEAH LYRA F. DELA CRUZ |  |  |  |  | CHANDA T. API | [5 empty] | CEZARIO JOEL C. ESPEJO
| Planning Officer I |  |  |  |  | Planning Officer IV/ Head, Policy Development and Planning Section |  |  |  |  | SWO IV/ OIC- Policy and Plans Division | [5 empty] | Regional Director